## Burndown
Project | 4th Iteration |  |  |  |  | 5th Iteration |  |  | 6th Iteration |  |  |  | 7th Iteration
Date | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
Total remaining bugs | 40 | 30 | 27 | 25 | 88 | 25 | 23 | 50 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | #REF! | 0
Total reminaing points | 53 | 52 | 49.5 | 49 | 62 | 74 | 74 | 25 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
Burnt points this week | 9 | 9.5 | 12 | 12 | 10 | 12.5 | 17.5 | 0 | 8 | 8 | 8 | 8 | #REF! | #REF! | #REF! | #REF!
Total burnt points | 9 | 18.5 | 30.5 | 42.5 | 52.5 | 65 | 82.5 | 82.5 | 90.5 | 98.5 | 106.5 | 114.5 | #REF! | #REF! | #REF! | #REF!
Discipline | Plan |  | Actual |  |  | Plan | Actual
Requirements | 38 |  | 53 |  |  | 7 | 6
Architecture | 9 |  | 1.5 |  |  | 7 | 4
Development | 7 |  | 10 |  |  | 29 | 11.5
Test | 0 |  | 10 |  |  | 7 | 0.5
Change Mangement | 5 |  | 5 |  |  | 7 | 0
Project Management | 1 |  | 4 |  |  | 7 | 0
General | 0 |  | 0 |  |  | 7 | 0

## Method Statistics
| Total | Role | Task | Work Product | Guidance
Requirements | 61 | 1 | 6 | 10 | 44
Architecture | 16 | 1 | 3 | 2 | 10
Development | 32 | 2 | 7 | 8 | 15
Test | 19 | 1 | 4 | 4 | 10
CM | 4 | 0 | 1 | 0 | 3
PM | 49 | 1 | 6 | 5 | 37
General | 14 | 1 | 0 | 0 | 13
Total | 195 | 7 | 27 | 29 | 132

## Requirements
| Committer: | Chris Sibbald, Telelogic |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
134895 | Artifact | Glossary | 1 | 5, 6 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
134895 | Template | Glossary | 1 | 5, 6 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
134915 | MethodPackage | Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Artifact | Use Case Model | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Term Definition | Requirement | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Writing Good Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Use Case | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Supporting Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Requirement Pitfalls | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Requirement Gathering Techniques | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Find and Outline Actors and Use Cases | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Detail Use Cases and Scenarios | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Guideline | Achieving Concurrence | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Checklist | Qualities of Good Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Concept | Traceability | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Concept | Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
135941 | Concept | Requirement Attributes | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
140073 | Artifact | Supporting Requirements | 3 | 5, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: RESOLVED
140073 | Template | Supporting Requirements | 3 | 5, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED
140073 | Guideline | Supporting Requirements | 3 | 5, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: RESOLVED
140073 | Checklist | Supporting Requirements | 3 | 5, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: RESOLVED
140073 | Concept | Supporting Requirements | 3 | 5, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: RESOLVED
140840 | Task | Define Vision | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
140844 | Task | Detail Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
140846 | Task | Find and Outline Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
140847 | Guideline | Achieving Concurrence | 2 | 5, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140848 | Guideline | Find and Outline Actors and Use Cases | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
140850 | Guideline | Use Case Formats | 2 | 6, 7 | 2006-06-14: NEW; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140852 | Guideline | Use Case Model | 2 | 6 | 2006-06-14: NEW; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140856 | Checklist | Use Case Model | 2 | 6 | 2006-06-14: NEW; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140858 | Checklist | Use Case | 2 | 6, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140859 | Checklist | Vision | 2 | 6, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140865 | Concept | Use Case | 2 | 6 | 2006-06-14: RESOLVED; 2006-06-21: RESOLVED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140867 | Checklist | Actor | 2 | 6, 7 | 2006-06-14: NEW; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
140871 | Artifact | ActorGoal List | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
141624 | Checklist | Qualities of Good Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143741 | Concept | Requirements | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Task | Find and Outline Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Task | Detail Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Task | Define Vision | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Artifact | Glossary | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Artifact | Use Case | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Artifact | Supporting Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Template | Supporting Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Template | Glossary | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Guideline | Use Case Formats | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Guideline | Achieving Concurrence | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Checklist | Use Case | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Checklist | Qualities of Good Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Concept | Use Case | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Concept | Supporting Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
143764 | Concept | Requirements | 1 | 4 | 2006-06-14: RESOLVED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
144235 | Guideline | Writing Good Requirements | 2 | 6, 7 | 2006-06-14: CLOSED; 2006-06-21: RESOLVED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
145773 | Guideline | Detail Use Cases and Scenarios | 2 | 6, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
145775 | Artifact | Use Case Storyboard | 1 | 5 | 2006-06-14: NEW; 2006-06-21: NEW; 2006-06-28: NEW; 2006-07-05: NEW; 2006-07-12: NEW; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
147349 | Concept | Use Case Model | 0.66667 | 5 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
147349 | Checklist | Use Case Model | 0.66667 | 5 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
147349 | Guideline | Use Case Model | 0.66667 | 5 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
147351 | Concept | Use Case Model | 2 | 6, 7 | 2006-06-14: ASSIGNED; 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
147354 | Artifact | Vision | 2 | 6, 7 | 2006-06-14: NEW; 2006-06-21: NEW; 2006-06-28: NEW; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
147356 | Role | Analyst | 1 | 5 | 2006-06-14: NEW; 2006-06-21: NEW; 2006-06-28: NEW; 2006-07-05: NEW; 2006-07-12: NEW; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
147431 | Artifact | Actor | 2 | 5, 7 | 2006-06-14: NEW; 2006-06-21: ASSIGNED; 2006-06-28: RESOLVED; 2006-07-05: RESOLVED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
147974 | CapabilityPattern | Manage Requirements | 4 | 5, 6 | 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED
149241 | Discipline | Requirements | 2 | 5, 6 | 2006-07-05: ASSIGNED; 2006-07-12: RESOLVED; 2006-07-19: RESOLVED; 2006-07-26: RESOLVED; 2006-08-02: RESOLVED
|  | Total Points | 90 |  | 43 | 47 | 33 | 25 | 21 | 21 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 8 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 15 | 21 | 12 | 8 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 16 | 2 | 11 | 17 | 19 | 19 | 19 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 23 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 23 | 24 | 15 | 10 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 16 | 17 | 14 | 14 | 13 | 13 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 38; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted points/ week |  |  | 2006-06-14: 32.5; 2006-06-20: 39; 2006-06-28: 46; 2006-07-05: 51; 2006-07-12: 53; 2006-07-19: 53; 2006-07-26: 53; 2006-08-02: 59
|  | Burnt Points / Week (adjusted) |  |  | 2006-06-14: 32.5; 2006-06-20: 6.5; 2006-06-28: 7; 2006-07-05: 5; 2006-07-12: 2; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 6
|  | Iteration Burndown |  |  | 5.5 | -1 | -8 | -13 | -15 | 7 | 7 | 1 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 53; 2006-07-26: Iteration Burndown:; 2006-08-02: 6; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0

## Architecture
| Committer: | Mark Dickson, Xansa |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
143180 | Role | Architect | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143181 | Task | Define Architecture | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143182 | Task | Refine Architecture | 2 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143183 | Task | Demonstrate Architecture | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143185 | Work Product | Architecture | 1 | 4 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143184 | Work Product | Architectural Proof-of-Concept | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143187 | Concept | Component | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
143191 | Guideline | Create Architectural Proof-of-Concept | 1 | 6 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
143192 | Guideline | Layering | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
143189 | Concept | Patterns | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143186 | Guideline | Analysis Mechanisms | 1 | 4 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143188 | Guideline | Design and Implementation Mechanisms | 1 | 4 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143193 | Guideline | Representing Interfaces to External Systems | 1 | 6 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
143178 | Guideline | Visual Modeling | 1 | 5 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
143179 | Guideline | Using Visualizations | 1 | 6 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
143195 | Principle | Using Patterns | 1 | 5 | 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
143194 | Principle | Abstracting Away Complexity | 1 | 5 | 2006-06-28: New; 2006-07-05: New; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
143190 | Checklist | Architecture | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147970 | Capability Pattern | Define Architecture | 1 | 5 | 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147971 | Capability Pattern | Determine Architectural Feasibility | 1 | 5 | 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
150761 | Discipline | Overview |  |  | 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 2 | 2 | 6 | 5 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 7 | 7 | 12 | 13 | 12 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 3 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 9 | 9 | 18 | 18 | 18 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 10 | 10 | 19 | 19 | 19.5 | 15.5 | 15.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 9; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted Points / week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 1.5; 2006-07-19: 5.5; 2006-07-26: 5.5; 2006-08-02: 5.5
|  | Burnt Points / Week (adjusted) |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 1.5; 2006-07-19: 4; 2006-07-26: 0; 2006-08-02: 0
|  | Iteration Burndown |  |  | 9 | 9 | 9 | 9 | 7.5 | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 1.5; 2006-07-26: Iteration Burndown:; 2006-08-02: 4; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0
Note on K11: Mark Dickson: Jim Ruehlin
Note on K12: Mark Dickson: Chris Doyle
Note on K13: Mark Dickson: Chris Doyle Content submitted for review
Note on K17: Mark Dickson: Jim Ruehlin
Note on K19: Mark Dickson: Chris Doyle Content submitted for review
Note on K21: Mark Dickson: Chris Doyle

## Development
| Committer: | Brian G. Lyons, Number Six Software, Inc. |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
145171 | Role | Developer | 1 | 4 | 2006-06-14: Assigned; 2006-06-20: Resolved; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
146946 | Role | Developer (vm) | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147148 | Task | Design the Solution | 2 | 4 | 2006-06-14: New; 2006-06-20: Assigned; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Reopened; 2006-07-26: Resolved; 2006-08-02: Resolved
147152 | Task | Design the Solution (vm) | 1 | 4 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147161 | Task | Implement Developer Tests | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147141 | Task | Implement Solution | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved
147171 | Task | Integrate and Create Build | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147166 | Task | Prototype the User Interface | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: New; 2006-08-02: New
147162 | Task | Run Developer Tests | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147149 | Work Product | Design | 1 | 4 | 2006-06-14: New; 2006-06-20: Assigned; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147153 | Work Product | Design (vm) | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147172 | Work Product | Build | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147163 | Work Product | Developer Test | 2 | 4 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147144 | Work Product | Implementation | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Resolved; 2006-08-02: Resolved
147154 | Work Product | Design Component | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147155 | Work Product | Use-Case Realization | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147167 | Work Product | UI Prototype | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: New; 2006-08-02: New
147176 | Concept | Refactoring | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147165 | Concept | Test First Design | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147177 | Concept | Continuous Integration | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147151 | Checklist | Design | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Assigned; 2006-08-02: Assigned
150638 | Checklist | Design (vm) | 2 | 6 | 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147150 | Guideline | Design | 3 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Resolved; 2006-07-05: Resolved; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147178 | Guideline | Continuous Integration | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147147 | Guideline | Implementation | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved
147173 | Guideline | Promoting Builds | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147174 | Guideline | Refactoring | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147169 | Guideline | User-Interface Prototype | 3 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: New; 2006-08-02: New
147164 | Guideline | Unit Test | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147157 | Guideline | Design Components Representation | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147158 | Guideline | Use-Case Realizations | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147156 | Concept | Entity Control Boundary Pattern | 3 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147973 | Capability Pattern | Develop Solution | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
149238 | Discipline | Overview | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
|  | Total Points | 60 |  | 56 | 55 | 49 | 46 | 47 | 49 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 30 | 28 | 24 | 15 | 17 | 16 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 1 | 2 | 3 | 10 | 9 | 10 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 1 | 4 | 7 | 8 | 7 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 31 | 30 | 27 | 25 | 26 | 27 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 56 | 55 | 52.5 | 52 | 53.5 | 27 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 7; 2006-07-26: Iteration 5 Target:; 2006-08-02: 29; 2006-08-23: Iteration 6 Target:; 2006-09-20: Iteration 7 Target:; 2006-09-27: 0
|  | Unadjusted Points/week |  |  | 2006-06-14: 0; 2006-06-20: 0.5; 2006-06-28: 3.5; 2006-07-05: 6; 2006-07-12: 6.5; 2006-07-19: 5.5; 2006-07-26: 9.5; 2006-08-02: 9.5
|  | Burnt Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0.5; 2006-06-28: 3; 2006-07-05: 3; 2006-07-12: 3.5; 2006-07-19: 2; 2006-07-26: 7.5; 2006-08-02: 2
|  | Iteration Burndown |  |  | 7 | 6.5 | 3.5 | 0.5 | -3 | 27 | 19.5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 10; 2006-07-26: Iteration Burndown:; 2006-08-02: 11.5; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0
Points per Iteration
[11 empty] | Iteration | Points
[11 empty] | 4 | 7
[11 empty] | 5 | 29
[11 empty] | 6 | 24

## Test
| Committer: | Brian G. Lyons, Number Six Software |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
146501 | Role | Tester | 1 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147182 | Task | Create Test Case | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
146937 | Task | Evaluate Test Results | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147183 | Task | Implement Tests | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
146940 | Task | Run Tests | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Assigned; 2006-08-02: Assigned
147184 | Work Product | Test Case | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147185 | Work Product | Test Data | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
146938 | Work Product | Test Log | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
146941 | Work Product | Test Script | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147194 | Concept | Test Ideas | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Resolved; 2006-08-02: Resolved
147188 | Concept | Types of Test | 3 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147195 | Checklist | Test Script | 1 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147186 | Checklist | Test Case | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147187 | Checklist | Test Data | 2 |  | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Resolved; 2006-07-19: Resolved; 2006-07-26: Resolved; 2006-08-02: Resolved
147189 | Guideline | Failure Analysis and Report Creation | 2 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved
147196 | Guideline | Maintaining Automated Test Suite | 2 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147198 | Guideline | Programming Automated Tests | 2 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
147191 | Guideline | Test Ideas | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved
147193 | Guideline | Test Suite | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Resolved; 2006-08-02: Resolved
| Capability Pattern | Test | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
| Discipline | Overview | 1 | 6 | 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
|  | Total | 37 | [5 empty] | 17 | 17 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 0 | 0 | 0 | 0 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 19 | 19 | 19 | 19 | 7 | 7 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 10 | 10 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 19 | 19 | 19 | 19 | 11 | 11 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 35 | 35 | 35 | 35 | 27 | 27 | 23.5 | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 0; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-08-30: 8; 2006-09-20: Iteration 7 Target:; 2006-09-27: 0
|  | Unadjusted Points / week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 10; 2006-07-19: 10; 2006-07-26: 10.5; 2006-08-02: 10.5
|  | Burnt Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 10; 2006-07-19: 0; 2006-07-26: 0.5; 2006-08-02: 0
|  | Iteration Burndown |  |  | 0 | 0 | 0 | 0 | -10 | 7 | 6.5 | 6.5 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 10; 2006-07-26: Iteration Burndown:; 2006-08-02: 0.5; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0
Points by Iteration
[11 empty] | Iteration | Points
[11 empty] | 5 | 9
[11 empty] | 6 | 8

## Change_Management
| Committer: | Chris Sibbald, Telelogic |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-21 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
134898 | MethodPackage | Change Management | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
136341 | Task | Request Change | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
136341 | Concept | Workspace | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
136341 | Guideline | Change Requests | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
136341 | Concept | Change Requests | 1 | 4 | 2006-06-14: CLOSED; 2006-06-21: CLOSED; 2006-06-28: CLOSED; 2006-07-05: CLOSED; 2006-07-12: CLOSED; 2006-07-19: CLOSED; 2006-07-26: CLOSED; 2006-08-02: CLOSED
147975 | CapabilityPattern | On-going Tasks | 3 | 5,6,7 | 2006-06-21: ASSIGNED; 2006-06-28: ASSIGNED; 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED
149236 | Discipline | Change Management | 3 | 5,6,7 | 2006-07-05: ASSIGNED; 2006-07-12: ASSIGNED; 2006-07-19: ASSIGNED; 2006-07-26: ASSIGNED; 2006-08-02: ASSIGNED
|  | Total Points | 11 |  | 0 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 0 | 3 | 3 | 6 | 1900-01-05 | 1900-01-05 | 1900-01-05 | 1900-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 5; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted Points / Week |  |  | 2006-06-14: 5; 2006-06-21: 5; 2006-06-28: 5; 2006-07-05: 5; 2006-07-12: 5; 2006-07-19: 5; 2006-07-26: 5; 2006-08-02: 5
|  | Burnt Points / Week |  |  | 2006-06-14: 5; 2006-06-21: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0
|  | Iteration Burndown |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 5; 2006-07-26: Iteration Burndown:; 2006-08-02: 0; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0

## Project_Management
| Committer: | Chris Armstrong, APG |  |  | Status
Bug | Item Type | Name | Points | Iteration | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
147965 | Capability Pattern | PM - Capability Pattern assess_and_close_out_project - create content | 2 | 5 | 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147967 | Capability Pattern | PM - Capability Pattern assess_and_plan_iteration - create content | 2 | 5 | 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147968 | Capability Pattern | PM - Capability Pattern initiate_project - create content | 2 | 5 | 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
147969 | Capability Pattern | PM - Capability Pattern manage_iteration - create content | 2 | 5 | 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146426 | Checklist | PM - Add new Checklist: Project Plan | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
151831 | Checklist | PM - Checklist: Iteration Plan - create | 2 | 6 | 2006-07-26: New; 2006-08-02: New
151834 | Checklist | PM - Checklist: Risk List - create | 2 | 6 | 2006-07-26: New; 2006-08-02: New
151832 | Checklist | PM - Checklist: Status Assessment - create | 2 | 6 | 2006-07-26: New; 2006-08-02: New
151835 | Checklist | PM - Checklist: Work Item List - create | 2 | 6 | 2006-07-26: New; 2006-08-02: New
146439 | Concept | PM - Add new Concept: Project Team | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146476 | Concept | PM - Concept: Building Effective Teams - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146436 | Concept | PM - Concept: Iteration - update content | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
151827 | Concept | PM - Concept: Metrics - update content | 2 | 6 | 2006-07-26: New; 2006-08-02: New
146437 | Concept | PM - Concept: Milestones - Add content | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146438 | Concept | PM - Concept: Phase - Update content | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146441 | Concept | PM - Concept: Risk - extend content | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146440 | Concept | PM - Concept: Risk - update content | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146482 | Concept | PM - Concept: Risk Management- update content | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
149235 | Discipline | PM - No project management discipline text. | 1 | 6 | 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146445 | Example | PM - Add new Example: Iteration Plan | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146444 | Example | PM - Add new Example: Project Plan | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146446 | Example | PM - Add new Example: Work Items List | 2 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
135397 | Guideline | PM - Add Content: Guideline: Work Item List | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146468 | Guideline | PM - Add new Guideline: Use Case Points Estimation Technique | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146500 | Guideline | PM - Add new Reference: Anchoring the Software Process | 1 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
151828 | Guideline | PM - Guideline: Assign Changes to an Iteration | 3 | 6 | 2006-07-26: New; 2006-08-02: New
146453 | Guideline | PM - Guideline: Assign Work - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146454 | Guideline | PM - Guideline: Estimation - update content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146455 | Guideline | PM - Guideline: Iteration Planning - update content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146456 | Guideline | PM - Guideline: Plan Project Phases - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146457 | Guideline | PM - Guideline: Prioritizing Work - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146459 | Guideline | PM - Guideline: Project Plan - add content | 3 | 4 | 2006-06-14: Closed; 2006-06-20: Closed; 2006-06-28: Closed; 2006-07-05: Closed; 2006-07-12: Closed; 2006-07-19: Closed; 2006-07-26: Closed; 2006-08-02: Closed
146460 | Guideline | PM - Guideline: Risk List - update content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146461 | Guideline | PM - Guideline: Staffing Project - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146463 | Guideline | PM - Guideline: Status Assessment - update content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146464 | Guideline | PM - Guideline: Time-Boxed Iterations - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146466 | Guideline | PM - Guideline: Type and Frequency of Assessments - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
146467 | Guideline | PM - Guideline: Types of Metrics - add content | 3 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
?? | Practice | Managing Risk
146477 | Practice | PM - Practice: Iterative Development - remove | 1 | 4 | 2006-06-14: Closed; 2006-06-20: Closed; 2006-06-28: Closed; 2006-07-05: Closed; 2006-07-12: Closed; 2006-07-19: Closed; 2006-07-26: Closed; 2006-08-02: Closed
151830 | Report | PM - Report: Iteration Burndown | 3 | 5 | 2006-07-26: New; 2006-08-02: New
151829 | Report | PM - Report: Project Burndown | 3 | 5 | 2006-07-26: New; 2006-08-02: New
151424 | Role | Project Manager | 1 | 5 | 2006-07-26: Assigned; 2006-08-02: Assigned
151782 | Task | Assess Results | 2 | 5 | 2006-07-26: New; 2006-08-02: New
151783 | Task | Close Out Project | 1 | 5 | 2006-07-26: New; 2006-08-02: New
151784 | Task | Initiate Iteration | 3 | 5 | 2006-07-26: New; 2006-08-02: New
151785 | Task | Plan Iteration | 2 | 5 | 2006-07-26: New; 2006-08-02: New
151426 | Task | Plan the Project | 2 | 5 | 2006-07-26: Assigned; 2006-08-02: Assigned
146502 | Task | PM - Task: Monitor and Control Project - update content | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
151824 | Template | PM - Template: Iteration Plan - replace | 2 | 5 | 2006-07-26: New; 2006-08-02: New
146504 | Template | PM - Template: Project Plan - replace | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: Assigned; 2006-08-02: Assigned
151826 | Template | PM - Template: Risk List | 2 | 5 | 2006-07-26: New; 2006-08-02: New
151837 | Template | PM - Template: Status Assessment - create | 2 | 5 | 2006-07-26: New; 2006-08-02: New
151836 | Template | PM - Template: Work Items List - create | 3 | 5 | 2006-07-26: New; 2006-08-02: New
151820 | Work Product | Iteration Plan | 2 | 5 | 2006-07-26: New; 2006-08-02: New
146503 | Work Product | PM - Add new Work Product: Risk List | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: New; 2006-07-26: New; 2006-08-02: New
151423 | Work Product | Project Plan | 2 | 5 | 2006-07-26: Assigned; 2006-08-02: Assigned
151821 | Work Product | Status Assessment | 2 | 5 | 2006-07-26: New; 2006-08-02: New
137120 | Work Product | Work Items List | 3 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
|  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  | 29 | 33 | 33 | 34 | 34 | 34 | 51 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assigned |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reopened |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resolved |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closed |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  | Remaining Bugs (New + Assigned + Reopened) |  |  | 30 | 34 | 34 | 35 | 35 | 35 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining Points |  |  | 62 | 62 | 62 | 63 | 63 | 63 | 98 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 1; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  | Unadjusted Points / week |  |  | 2006-06-14: 4; 2006-06-20: 4; 2006-06-28: 4; 2006-07-05: 4; 2006-07-12: 4; 2006-07-19: 4; 2006-07-26: 4; 2006-08-02: 4
|  | Burnt Points / Week |  |  | 2006-06-14: 4; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0
|  | Iteration Burndown |  |  | -3 | -3 | -3 | -3 | -3 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 4; 2006-07-26: Iteration Burndown:; 2006-08-02: 0; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0

## General
|  | Committer: | Steve Adolph, UBC | Points | Iteration | Status
| Bug | Item Type | Name |  |  | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
| 133269 | Concept | Stakeholder | 4 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
| 138784 | Concept | General - Need content for Focus principle | 4 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
| 140019 |  | General - Navigation Map | 8 | 5 | 2006-06-14: Re-openned; 2006-06-20: Re-openned; 2006-06-28: Re-openned; 2006-07-05: Re-openned; 2006-07-12: Re-openned; 2006-07-19: Re-openned; 2006-07-26: Re-openned; 2006-08-02: Re-opened
| 145669 | Guideline | General - Improve Guidelines for Referencing Tasks | 8 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
| 145670 | Guideline | General - Improve Guidelines for Writing Guidances in Plu... | 4 | 6 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
| 145671 | Guideline | General - Indicate UML Prefered Diagramming Language in P... | 2 | 5 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: Assigned; 2006-07-26: Assigned; 2006-08-02: Assigned
| 146449 |  | General - Guidance: Copyright | 4 | 5 | 2006-06-14: Re-openned; 2006-06-20: Re-openned; 2006-06-28: Re-openned; 2006-07-05: Re-openned; 2006-07-12: Re-openned; 2006-07-19: Re-openned; 2006-07-26: Re-openned; 2006-08-02: Re-opened
| 146487 | Supporting Material | General - Glossary - seems a little light | 12 | 7 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: new; 2006-07-26: new; 2006-08-02: new
| 146489 | Supporting Material | General - Index seems light | 12 | 7 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 146491 |  | General - Graphic banner - replace | 4 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 146493 |  | General - About dialog box - inconsistent text | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 146494 |  | General - index/content.htm - title tag | 1 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 146499 |  | General - Create OpenUP graphics | 4 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 147135 | Supporting Material | General - OpenUP White papers explaining core concepts ar... | 80 | 7 | 2006-06-14: Assigned; 2006-06-20: Assigned; 2006-06-28: Assigned; 2006-07-05: Assigned; 2006-07-12: Assigned; 2006-07-19: ASSIGNEDASSIGNED; 2006-08-02: Assigned
| 150766 | Role | General - Review Any Role usage. | 2 | 5 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 150767 | Supporting Material | General - Create Getting Started Supporting Material | 25 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 150768 | Supporting Material | General - Create Overivew | 25 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 150769 | Supporting Material | General - Review and update references | 5 | 7 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 150770 | Phase Iteration Template | General - Review phase iteration templates | 5 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 150771 | Work Product Kind | General - Policy for Work Product Kind must be established | 5 | 6 | 2006-06-14: New; 2006-06-20: New; 2006-06-28: New; 2006-07-05: New; 2006-07-12: New; 2006-07-19: NEW; 2006-07-26: NEW; 2006-08-02: NEW
| 152354 |  | Re-architecting and Re-positioning OpenUP |  |  | 2006-07-26: New; 2006-08-02: New
Where do these belong???
|  | Guideline | Conduct Review/Concurrence
|  | Concept | Prototype
|  | Capability Pattern | Assess and Close Out Project
|  | Capability Pattern | Assess and Plan Iteration
|  | Capability Pattern | Initiate Project
|  | Capability Pattern | Manage Iteration
|  |  | Unconfirmed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | New |  |  | 2006-06-14: 15; 2006-06-20: 15; 2006-06-28: 14; 2006-07-05: 12; 2006-07-12: 17; 2006-07-19: 17; 2006-07-26: 17; 2006-08-02: 18
|  |  | Assigned |  |  | 2006-06-14: 7; 2006-06-20: 7; 2006-06-28: 7; 2006-07-05: 7; 2006-07-12: 6; 2006-07-19: 7; 2006-07-26: 7; 2006-08-02: 7
|  |  | Reopened |  |  | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Resolved |  |  | 3 | 3 | 7 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Verified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Closed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 2006-06-14 | 2006-06-20 | 2006-06-28 | 2006-07-05 | 2006-07-12 | 2006-07-19 | 2006-07-26 | 2006-08-02 | 2006-08-09 | 2006-08-16 | 2006-08-23 | 2006-08-30 | 2006-09-06 | 2006-09-13 | 2006-09-20 | 2006-09-27 | 2006-10-04
|  |  | Remaining Bugs (New + Assigned + Reopened) |  |  | 22 | 22 | 21 | 20 | 25 | 25 | 24 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Remaining Points |  |  | 154 | 154 | 154 | 154 | 154 | 74 | 74 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Targeted Points/ Iteration |  |  | 2006-07-05: Iteraton 4 Target:; 2006-07-12: 0; 2006-07-26: Iteration 5 Target:; 2006-08-02: 7; 2006-08-23: Iteration 6 Target:; 2006-09-20: Iteration 7 Target:; 2006-09-27: #REF!
|  |  | Unadjusted Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0
|  |  | Burnt Points / Week |  |  | 2006-06-14: 0; 2006-06-20: 0; 2006-06-28: 0; 2006-07-05: 0; 2006-07-12: 0; 2006-07-19: 0; 2006-07-26: 0; 2006-08-02: 0
|  |  | Iteration Burndown |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
|  |  | Burnt Points / Iteration |  |  | 2006-07-05: Iteration Burndown:; 2006-07-12: 0; 2006-07-26: Iteration Burndown:; 2006-08-02: 0; 2006-08-23: Iteration Burndown:; 2006-08-30: 0; 2006-09-20: Iteration Burndown:; 2006-09-27: 0